## Sheet1
ACTIVITY | DEADLINE | RESPONSIBILITY | NOTES (UPDATED) | A | S | O | N | D | J | F | M | A | M | J | J
Establish GCRF Board | 2018-09-01 | DIRECTOR R&IS | Complete | bar: S
Agree ToRs, business cycle and GCRF QR Strategy QR plan | 2018-10-01 | DIRECTOR R&IS | Complete | bar: O
Launch 2018-19 GCRF QR funding competition for TU Staff | 2018-10-01 | RIS FUNDING MGR | Relaunched DEC with Associate Dean support following poor and non compliant response | bar: O; D
Assess 2018-19 GCRF QR Funding Applications against criteria and compliance requirements | 2018-11-01 | GCRF BOARD | see above | bar: N; J
Allocate 2018-19 GCRF QR Funds | 2018-11-01 | GCRF BOARD | see above | bar: N; J
Review progress of 2019-19 GCRF QR projects with principal investigators in terms of compliance, expenditure, and progress to 31 July 2019 | 2019-02-01 | GCRF BOARD | Complete | bar: F
Prepare Interim Monitoring review | 2019-03-01 | RIS FUNDING MGR | Complete | bar: M
Submit interim Monitoring Review with VC approval | 2019-04-01 | DIRECTOR R&IS | RE wanted clarifiactions in July - resubmitted | bar: A; J
Request PIs to prepare review material for 2018-19 GCRF QR Project Review, and 2019-20 funding competition | 2019-07-01 | RIS FUNDING MGR | Complete | bar: J
Send out annual review requirements to PIs and FCD | 2019-08-01 | RIS FUNDING MGR | Complete | bar: A
Financial review of 2018-19 expenditure | 2019-09-01 | DEPUTY DIRECTOR FINANCE (FCD) | bar: S
Review outcomes and impacts with PIs | 2019-09-01 | RIS IMPACT MGR | bar: S
Prepare Annual Monitoring Review | 2019-09-01 | RIS FUNDING MGR | bar: S
Submit Annual Montoring Review | 2019-10-01 | DIRECTOR R&IS | bar: O
Conduct 2018-19 GCRF QR Project Review to include project presentations on outcomes, impact, lessons learnt, and possible next steps as well as 2019-20 GCRF QR Funding Competition | 2019-10-01 | GCRF BOARD | bar: O
Refine the GCRF QR Strategy in terms of geographical focus of DTA Countires involved, GCRF challenge areas and SDGs. | 2019-10-01 | GCRF BOARD | bar: O
Update TU GCRF QR web pages with case studies and run a University Update news report | 2019-10-01 | RIS FUNDING MGR | bar: O
Review GCRF Board ToRs, business cycle, implementation plan and membership | 2019-11-01 | DIRECTOR R&IS | bar: N
Deliver training to Board, GCRF PIs, and academic staff on logic chain theory | 2019-11-01 | DIRECTOR R&IS | bar: N
Review Bids for 2019-20 GCRF QR | 2019-11-01 | GCRF BOARD | bar: N
Conduct compliance checks with PIs and international partners | 2019-12-01 | RIS FUNDING MGR | bar: D
Allocate 2019-20 GCRF QR Funds | 2019-12-01 | GCRF BOARD | bar: D
GCRF Board to develop contribution for TU2025 international research strategy | 2019-12-01 | CHAIR GCRF BOARD | bar: D
Review project progress, compliance and financial forcast with PIs | 2020-03-01 | CHAIR GCRF BOARD | bar: M
Prepare Interim Monitoring review | 2020-03-01 | RIS FUNDING MGR | bar: M
Submit interim Monitoring Review with VC approval | 2020-04-01 | DIRECTOR R&IS | bar: A
Review potential partnership opportunitiies for 2022-21 onwards | 2020-05-01 | GCRF BOARD | bar: M
Develop Partnership Templates based on sector best practice | 2020-05-01 | RIS FUNDING MGR | bar: M
Request PIs to prepare review material for 2018-19 GCRF QR Project Review, and 2020-21 funding competition | 2020-06-01 | RIS FUNDING MGR | bar: J
Send out annual review requirements to PIs and FCD | 2020-07-01 | DIRECTOR R&IS | bar: J
Financial review of 2018-19 expenditure | 2020-08-01 | DEPUTY DIRECTOR FINANCE (FCD) | bar: A
Prepare Annual Monitoring Review | 2020-09-01 | RIS FUNDING MGR | bar: S
Submit Annual Montoring Review | 2020-10-01 | DIRECTOR R&IS | bar: O
Launch 2020-21 GCRF QR funding competition for TU Staff | 2020-11-01 | RIS FUNDING MGR | bar: N
Assess 2020-21 GCRF QR Funding Applications against criteria and compliance requirements | 2020-12-01 | GCRF BOARD | bar: D
Allocate 2020-21 GCRF QR Funds | 2020-12-01 | GCRF BOARD | bar: D
Review progress of 2020-21 GCRF QR projects with principal investigators in terms of compliance, expenditure, and progress to 31 July 2019 | 2021-02-01 | GCRF BOARD | bar: F
Prepare Interim Monitoring review | 2021-03-01 | RIS FUNDING MGR | bar: M
Submit interim Monitoring Review with VC approval | 2021-04-01 | DIRECTOR R&IS | bar: A
Draft and submit the 2021-24 GCRF QR Strategy | 2021-06-01 | DIRECTOR R&IS | bar: J
Request PIs to prepare review material for 2020-21 GCRF QR Project Review, and 2019-20 funding competition | 2021-07-01 | RIS FUNDING MGR | bar: J
Send out annual review requirements to PIs and FCD | 2021-08-01 | RIS FUNDING MGR | bar: A
Financial review of 2018-19 expenditure | 2021-09-01 | DEPUTY DIRECTOR FINANCE (FCD) | bar: S
Prepare Annual Monitoring Review | 2021-09-01 | RIS FUNDING MGR | bar: S
Submit Annual Montoring Review | 2021-10-01 | DIRECTOR R&IS | bar: O
Conduct 2018-19 GCRF QR Project Review to include project presentations on outcomes, impact, lessons learnt, and possible next steps as well as 2019-20 GCRF QR Funding Competition | 2021-10-01 | GCRF BOARD | bar: O